ERASMUS + KA2 2018/2020

ISTITUTO COMPRENSIVO “GALILEO GALILEI” San Giovanni Teatino

|  |  |
| --- | --- |
| Main objective | Exchange of Good Practices(scambio delle buone prassi)) |
| Project Title | Finding European Identity through Education and Intercultural Dialogue betweenEuropean Citizens |
| Project Start Date | 01/09/2018 |
| Project Total Duration | 24 months |
| Language used | English |
| Coordinator country | Poland (Czestochowa) |
| Partners | Romania(Bucarest),Italy,Portugal(Baixa da Banheira),Lithuania(Kraziai),Spain(Torrevieja) |
| Main topics | Cultural heritage/EuropeanYear of Cultural heritage – Inclusion - Equity |
| Mobilities | **October 2018** ,**Poland**(only for coordinators)  **February 2019,Lithuania** (4 days) Student’s motivation,cooperation and self-esteem training for teachers……..3 teachers  **April 2019,Italy** (students and teachers) “Footsteps of regional and national culture”,(6 days), 34 participants….  **June 2019,Spain** (students and teachers) “Experience my culture”-workshops (6 days)…(total number of Italian participants 9)  **November 2019**,Romania(students and teachers) “Let’s play a game”-discovering cultural heritage by using modern technology and sport of the past) (Italian participants n.9)  **April 2020,Portugal** (only for teachers), n.3 teachers “The modern face of cultural heritage” – modern technology in discovering culture…..  **June 2020,Poland** (students and teachers)”Let’s meet in Poland”- the map of Europe ,Italian participants n.9. |
| Activities | **September** :”Let’s meet in Europe”  The aim is to familiarize with the basic aspects of culture -names and finding out information about the most popular names in each country – also equivalents in European languages of our partners.Creation of a poster.  **October** : Coordinators meeting  **November** :Creating official project website by Romania- participating in a competition on a common project logo …..  **December** : postcards and Christmas wishes will be sent ….each country will record three carols (in a native language,English and in one language of our partner),Carols will be recorded on a CD and exchanged.  **January 2019** :The art and photo album will be created in each country to show the diversity of Europe in terms of location and Geography features, the names of the countries will be written in all six countries.  **March 2019** :”The legend of my city or region” it is the project based on the meeting with an expert(from the City Library , or a historian), who is invited by each school.During the lecture , students listen and draw pictures,illustrations.Their follow-up activity is to write the legend and provide visual aspects-pictures.Students will exchange the legends and translate them in English ….They will be sent to schools and be posted on the official website.  **April 2019** : “Footsteps of regional and national culture”- Italian experience  **May 2019** : “A trip of the past” task is carried out with the help of the National Archives or Town Hall. Students gather information about the places of cultural heritage in the city or region.Three places are chosen and students create a map,locate the places and compare their look and the purpose of use within the last hundred years. This mapi s converted into an interactive one and will be used in the following mobilities……  **June 2019** : “Experience my culture”- workshops |